## Bugs
2022-08-04
Should not accept duplicate email id
Reset pass: New pass and Confirm pass should be same, accepting different text
Login: Should only accept registered Email Id. If not registered than user should get message to mail id not registered.
Forgot pass: Clicking on Forgot pass should redirect to mail; from mail user can get the Reset password link; by which user can reset the pass.
2022-08-05
Create pass: User is not able to uncheck the checked box
Unique Id: Not have any option to reset the Unique id
Confirm Unique Id: User is able to click on 'continue' button without checking the checkbox
After successfully creating the wallet; Clicking on Done button redirects back to Confirm Unique ID page
Forgot pass: Shift the title 'Forgot Password' to downward * Verification is spelled incorrectly as 'verification' and also replace comma by period sign.
Reset pass/ Create pass: Eye icon is missing |  | Not added to Jira
Reset pass: If the new pass is same as the previous pass, system should throw an error message and didn't accept that
After reset pass getting 'Let's sign you in' page after that getting page verification success
2022-08-09
Application is taking time to start/load
Create pass and Reset pass field has only 1 eye icon
2022-08-10
Register Yourself: Email ID should not be case sensitive
OTP Verification>Resend OTP: User is not able to enter the new OTP over old one |  | NAB
2022-08-11
Admin panel>LogIn: Email ID should not be case sensitive
Admin panel>User List: 'Updated At' column list need sorted validation
Login: User is getting "Successful Login" message after trying with incorrect credential.
2022-08-12
All the Info messages/error message should be center aligned. (Check Unique ID pages)
Remove blue color from Blank checkbox in Create password and Confirm Unique ID page
OTP code should not be in dotted form.
the wallet created successfully animation page
2022-08-17
Swap: 'To' block is appearing in darker shade; color should only change when focus shift to the particular field.
Swap: User is not able to scroll the page when user focus is on 'From'/'To' field (or when the keypad is open on screen)
Sap> Swipe to Confirm: In place of "Swipe to Confirm" button, only the 'Confirm' button is available | need to confirm from dev
Swap>Insufficient> In Swap detail, In place of 'WETH', it should be 'BUSD' (minor UI)
Swap> Insufficient balance: Error message "Insufficient ETH Balance" is getting out of the highlighted area.
Settings> Network: Ethereum is spelled incorrectly as 'Etherium'
2022-08-18
Send: Lines after search box and account is missing Send> Input: Lines under the transaction detail is missing | PICO-87
Send(Global): Header colour is mismatched | PICO-86
Send: Ethereum logo is missing | PICO-96
Send> Input: Increase the font size of title text and decrease font of placeholders present on To and Send field | PICO-88
Send> Input: The highlighted USD value should not be in bold | PICO-89
Send> Confirm: Account address should be minimise as per space | PICO-90
Send> Confirm: Accepting negative value in Send field | PICO-91
Send> Confirm: Incorrect error message | PICO-92
Send: Functionality of 'Back' and 'Cancel' button is same | PICO-93
2022-08-19
Admin panel>User List> Email: Getting Email status as verified with incomplete Signup process | PICO-94
Admin panel> Reset Password: Sentence 'Click here to Login' is getting merge with 'Confirm OTP' button | PICO-95
Send: Token logo is missing | PICO-96
Token amount and Wallet address is taking long time to appear on screen | PICO-99
User is receiving incorrect Wallet details. | PICO-100
2022-08-22
Send> Confirm: User is getting Sending transaction failed message on every transaction | PICO-109
Settings>Account Security>Offline Mode>Unique ID: Unique ID is getting overlap with warning message | PICO-114
2022-08-23
Settings> Join Community: Decrease the font size of text "Join Community" | PICO-120
Setting> Account Security: Difference in Offline mode icon | PICO-121
Setting> Account Security: Toggle button should be in Blue | PICO-124
Setting> Account Security>Offline mode: User is not able to activate Online mode at same time when he activated the Offline mode. | PICO-125 and PICO-126
Setting> Account Security: "Activate Online/Offline mode" text and "Activate/Cancel" button text should be bold.
Setting> Account Security(Global): Adjust the page content as per the device space . | PICO-122
Setting> Account Security> Unique ID: Eye icon of show/hide is missing in Unique Id field. | PICO-123
Login: Replace the Login text with loader icon | PICO-127
2022-08-24
Send: The transaction(Send) took place from previously logged User address- High priority | PICO-134
Send>Confirm: Send button is going out of the screen | PICO-135
Settings>Account Security>Offline Mode>Unique ID: Unique ID is getting overlap with warning message | PICO-116- Reopen
Send>Input: Content are not aligned as per figma
2022-08-26
Receive>Main screen: Space is missing below and above QR code | PICO-138
Receive>Main screen: Increase the size of the Wallet address field | PICO-138
Receive>Select assets: Search field functionality is missing and token icon | PICO-139
Receive Enter Amount: Text are not aligned inside the input field | PICO-140
Receive>Receive Asset: Copy icon is incorrect | PICO-141
Receive: Receive, back, done functionality is missing | PICO-142
Receive: Receive Page header is overlapping with phone header | PICO-142
2022-08-29
Receive Asset:The content "Scan the QR code to receive" is overlapping with the header text 'Receive' and 'Done' when user try to select the address | PICO-143
Receive Asset: Functionality of Copy and share icon is missing | PICO-146
Receive>Select Asset: Not able to see the Assets list for first time | PICO-145
Receive> Enter Amount: As per figma 'Cancel' button should be present in place of 'Done' The cursor should be in black color | PICO-144
2022-08-31
REceive>Final page: Functionality of Copy and Share button is missing | PICO-153
Page header is moving above the screen | PICO-157
Send>Send amount: 'Send; button is not aligned on center | PICO-154
Homepage: Increase the size of Arrow icon and Receive text for receive button | PICO-155
In Offline mode user went to the transaction page , not able to send token but getting the 'Send process' without any error message for offline mode | PICO-152
Receive>Enter Amount: Token icon is not present on Enter amount field | PICO-156
2022-09-01
Receive(Global): Page header is missing | PICO-158
Receive>Token list: BNB logo
Receive>Enter Amount: Reset functionality
Increase the size of page content like address
Receive button functionality on last page
Unique Id: Keyboard should go back from screen after clicking on page
Offline mode: When comes to offline homepage, bottom menu have only Wallet, Browser, Swap and Settings option | PICO-161
Settings(Global): Increase the size of text 'Settings' present on page header | PICO-160
Homepage>Send: Clicking on 'Send' button, navigates to send page. Page redirect back to homepage. | Old cred
Send>Scan QR: User is not able to scan the QR code except PICO Wallet | PICO-159
2022-09-02
Receive>Request>Token list: GMT contract address is present in place of token symbol
Receive>: Reset functionality
Receive button on Receive last page
Id created Successful page is breaking
2022-09-08
Swap:Border is missing for 'From' section initially as shown in figma
Swap: For "To" field the token selected in field "From" should be disable
Some UI changes: Main Screen: Change the color of Send, Receive and Buy Circle area as per figma Main Screen: "Ethereum Mainnet" area should be centralized Main Screen: Icons size are not same on Bottom navigation bar Main Screen: Increase the icon size present on app header like Pico bird, setting and Scanner
2022-09-13
Create password: Text 'Password must be at least 8 characters' need slight spacing
Send> Token search: Back button is not working
Global: Page content should shift slightly up
MAin Screen: Increase the size of the oval "Ethereum Mainnet" nackground to adjust the arrow icon
Settings: Wallet, Reddit and Network image is not clear Settings> Networks: tron wallet and Exodus
2022-09-14
Buy>Purchase method(Global): Page colour mismatched. On-Ramper area should be in White and complete page should be in gray color as per figma | PICO-249
Buy>Amount to Buy: User should not able to place cursor before Zero | PICO-250
Buy>Amount to Buy: PIco logo is missing from Main Wallet area | PICO-251
Buy>Amount to Buy: $ is missing from entering amount | PICO-252
Buy>Amount to Buy: User is not getting the selected token values after entering the amount to buy Some time the values didn't change after increasing the amount. After decreasing the value the functionality is working fine. | PICO-254
Buy>Amount to Buy: Complete page should be in gray except the Main wallet area. Main wallet area should be rectangle with oval corners. | PICO-251 PICO-249
Buy>Amount to buy: Space between usd amount and token value is more as per figma | PICO-253
Create Password: Functionality of eye icon is incorrect
2022-09-15
Swap>Confirm: back button press kerne se app se bahar ja rahe hai
Approve token' page should go back to swap page not to homescreen
Swap: Token Balance and the approximate values of the entered amount in USD are static values
Address book: Clicking on back button of device didn't move the page on back screen
Swap>Confirm: "Confirm Swipe" button is present on Confirm page
Swap: User is able to enter the space, coma and multiple dots in 'To' field, which is incorrect
2022-10-03
iOS: First screen of PICO app is appearing in White | PICO-342
Homepage: mobile header is not visible as appearing everithing black | PICO-341
MAin Screen: Content are misaligned | PICO-339
Main screen: PICO logo and icons are disappearing from screen. | PICO-340
On Scanning QR code, a square box to fix the scan area should appear | PICO-343
If user exit the pico app and reopen the app, it redirects to same page instead of login credentials. | PICO-344
2022-10-04
Settings>Wallet: Pico Bird icon is missing in main wallet
Settings>Account Security>Offline mode: User is not able to write Unique ID When user try to switch to Offline mode and click Activate button and try to write the Unique ID, user didn't able to write any thing or keyboard did not appeared
Swap> Advanced settings: Custom is spelled incorrectly as 'Custon' | PICO-353
Swap> Advanced settings: highlighted text below Reset button should be in white | PICO-353
Swap> Advanced settings: As per figma highlighted/focus text should be in black | PICO-353
Swap> Advanced settings: Back button is not working for Advance setting popup | PICO-352
Swap> token name is moving out of the box | PICO-356
Swap>Swap to Confirm: Toggle switch blue from outside and the button should be in light blue as per figma
Swap: Done button is missing in swap keypad | PICO-354
Loading page is appearing in black for light mode and for dark mode it is appearing in white
Send: Place holder for 'Send' field is incorrect as per choosen network
Receive>Request: Back button is not working on single click
Swap: User is not able to swipe back to the first page of Swap
Swap: When user try to switch dark to light mode, the text field area remains in dark mode (vice-versa)
Buy: In both light and dark mode, 'Onramper' logo is missing in Buy Crypto first page.
Buy: In both light and dark mode, highlighted networks list are truncating from bottom in Search token page
Buy: In both light and dark mode, Pico bird is missing from main wallet logo Enter amount area is misaligned, $ and amont need adjustment
In bottom nav bar, 'Browser' and 'Swap' is not working on single touch
Global: In header, the 'Back' or 'settings' button need to be center aligned.
When user try to scan QR code, the PICO wallet got Crash.